## Slide 1
Click to add title
Elygrid Project (Grant Agreement nº 278824)
Pablo Marcuello Foundation for the Development of New Hydrogen Technologies in Aragon (Spain)
www.elygrid.com

## Slide 2: PROJECT OVERVIEW
Improvements to Integrate High Pressure Alkaline Electrolysers for Electricity/H2 production from Renewable Energies to Balance the Grid
SP1-JTI-FCH.2010.2.1 Efficient alkaline electrolysers
Duration 38 months, from 01/11/2011 to 31/12/2014
Budget: 3.701.178,33 € / Funding: 2.105.017,00 €
Goal: improve TCO of MW alkaline electrolysers
Project in the last two moths

## Slide 3: PROJECT TARGETS AND ACHIEVEMENTS

## Slide 4: PROJECT TARGETS AND ACHIEVEMENTS
Status before project | AIP target | Project Target | Current status/achievementS | Expected final achievement
SoA (2011) -> 1,6 T/d | 2015 target: Unit capacity (Ton/d) = 1,5 | Double current density -> double unit capacity | 3 Ton/d with current density tested under Elygrid project | 100
SoA (2011) -> 70% stack efficiency | 2015 target: Efficiency = 68% | 10% increase stack efficiency | 70% with previous technology 66% with new technology at double current density | 90
SoA (2011) -> > 3 | 2015 target: Cost (M€/(T/d)) = 2.8 | 25% cost reduction | Assessment of the last BOP improvements | 100
MAIP objectives:

## Slide 5: PROJECT TARGETS AND ACHIEVEMENTS
Status before project | AIP target | Project Target | Current status/achievementS | Expected final achievement
0.18 A/cm2 | 0.75 A/cm2 with 80% HHV | 0. 5 A/cm2 | 0. 3-0.4 A/cm2 | Stable operation
25 year lifespan | 10 year lifespan | 10 year lifespan | Depend on the membrane | 75
SoA (2011) -> > 3000 €/Nm3 | 3000€/Nm3for a complete system | 25% cost reduction | Assessment of the last BOP improvements | 100
SoA (2011) -> 33 bar | Operating pressure >150 bar | Not applicable to this project | Hydrogen pressure is considered high enough | 100
AIP objectives:

## Slide 6: PROJECT TARGETS AND ACHIEVEMENTS
Chart: Potebntial U / V
Asbestos | 1.99 | 1.98 | 2.15 | 2.09 | 2.1
Barite thin (500 micron) | 1.82 | 1.85 | 1.84 | 1.82 | 1.85

## Slide 7: RISKS AND MITIGATION
Objective target: Efficiency = 68% and 0.75 A/cm2 with 80% HHV
Bottlenecks and risks: unspecified in MAIP (not related to A/cm2) Better defined in the topic (0,75 A/cm2) The project agreed an increase of the stack efficiency of 10% related to the previous technology (achieved with the new technology) and a current density of 0, 5 A/cm2. The project has already tested the unit at 0,4 A/cm2 and it is possible to test at 0,5 but it is not considered as a priority.
Revision of targets: No
Objective target: 10 year lifespan
Bottlenecks and risks: It will depend of the lifespan of the membrane. All the other components have higher lifespan but it is difficult to assure that a material developed under the project can have 10 year lifespan.
Revision of targets: No

## Slide 8: RISKS AND MITIGATION
Objective target : Operating pressure >150 bar
Bottlenecks and risks: This target was mentioned in the topic but not in the project targets. In any case, as electrolysis study remarks, an output pressure of 33 bar is considered a good level of operation.
Revision of targets: No
Objective target: Retention of >90% of initial efficiency over at least 1000 on/off switching cycles
Bottlenecks and risks: The testing of new technology at constant operation has been longer than initially expected and it is possible that more tests with new materials at constant operation are needed. For the project, it is priority to find the best material before testing at discontinuous operation.
Revision of targets: Yes
Suggested nature of revision: It is priority to find the best material before testing at on/off cycles.

## Slide 9: SYNERGIES WITH OTHER PROJECTS AND INITIATIVES
  EMPA obtained a Swiss internal project granted by BFE which is a public funding institution (Bundesamt/federal office of Energy).
  FHA has co-funded with another national project called DESPHEGA which is also related to alkaline electrolysers. The project was granted in the framework of INNPACTO call (Department of Economics and Competitiveness, Spain)
  Contacts done with RESelyser project (FCH-JU) and final event for sharing public results, expectations and possible further collaboration

## Slide 10: HORIZONTAL ACTIVITIES
Training and education
  Different post-doc and PhD students are working in the project in different WPs: membrane development, power electronics and balance of plant optimization
Safety, Regulations, codes and standards
  The project has developed a document with the main regulations, codes and standards which must be taken into consideration in order to design an electrolyser. This document will be public.
Public awareness
  The project has a website www.elygrid.com where all general information, news and public papers and presentations can be downloaded

## Slide 11: DISSEMINATION ACTIVITIES
Conference presentations
  Elygrid Project presents in the: IPHE Workshop Seville, November 2012. 4th EUROPEAN PEFC & H2 FORUM, July 2013. International Conference on Hydrogen Safety 2013, September 2013. Review days (2011-2014). 8TH International Symposium Hydrogen & Energy, February 2014. EUROPEAN HYDROGEN ENERGY CONFERENCE 2014, March 2014. WHEC 2014 (two oral presentations&one poster). Iberconnapice, October 2014.
Workshops organized by the project
  The project attended the workshop called “Water electrolysis day” organized by the FCH-JU
  Final event at the end of the project with RESelyser project
Publications
  LCA papers: previous analysis and final results
  Paper from modeling results and BOP optimization

## Slide 12: EXPLOITATION PLAN/EXPECTED IMPACT
“go-to-market” Target: validation of improved technology with a several MW electrolyser unit size at competitive price
Notes: What has your project changed in the panorama of FCH technology development and/or commericalisation? -> high capacity elys at competetive price
How will the project’s results be exploited? When? By whom? -> electrolyser manufacturer and partners
RTD projects:
  What are the main results that go beyond international state-of-the art? – high capacity per stack at low cost
  What are the achievements that will allow progressing one step further to cost reductions and enhanced performance (efficiency, durability)?
  How can the results from your project be taken on-board by industry? -> by the industry partners inside the consortium
Demonstration projects:
  What are the next stages, after project ends to make commercial impact or achieve MAIP targets?
Cross-cutting:
  What are the main achievements going with TRL increase? (test standardisation, safety assessment etc.)

## Slide 13: EXPLOITATION PLAN/EXPECTED IMPACT
Notes: What has your project changed in the panorama of FCH technology development and/or commericalisation?
How will the project’s results be exploited? When? By whom?
RTD projects:
  What are the main results that go beyond international state-of-the art?
  What are the achievements that will allow progressing one step further to cost reductions and enhanced performance (efficiency, durability)?
  How can the results from your project be taken on-board by industry?
Demonstration projects:
  What are the next stages, after project ends to make commercial impact or achieve MAIP targets?
Cross-cutting:
  What are the main achievements going with TRL increase? (test standardisation, safety assessment etc.)